## PivotTable
Row Labels | Count of Tenative Date
Arrest Report | 1
Booking | 1
CAD Incident
Case Transfer
Case-Charge Updates | 1
CaseChargeFiling | 1
CCH Query
Court Event | 1
Court Order | 3
CrimeLabRequestResults | 1
Incident (Offense) Report | 1
Motions and Proposed Orders | 1
New Case Initiation | 1
Pre-Trial Assessment (Probation Status)
Public Safety Assessment (PSA) | 1
Release | 1
Return Of Service | 2
RosterUpdate
Subpoena | 1
Uniform Charge Table Update | 1
UniformCommitmentOrder | 1
VictimNotification | 1
Warrant Issued | 2
Warrant Query
Warrant Request
Warrant Update | 1
(blank)
Grand Total | 23

## Pub-Sub Matrix
Subscriber(s)
# | Chron-ological Order | Implementation Priority (LMH) | Implementation Order | Critical Path | IEPD Published-Tenative Date | API-ExchangeDataType | Business Process | Publishing System | Publishing System2 | Publishing System3 | Triggering Event | DigiCourt-Muni | District Court CMS | DigiCourt-Juvenile | JMS | Pre-Trial Services | Prosecutor by Karpel | DefenderData | RMS | CloudGavel | CourtNotify | CASTNet | City Attorney (future) | LIMS (future) | evidence.com (future) | LACCH (future) | Dept. of Corrections (Future) | Roadmap Reference | As-Is BPMN-Data Object | PM Input/ Questions | Notes | GitHub Page
2 | 4 | H | 1 | Y | 2024-06-25 | Booking | Booking | JMS |  |  | CINTAP review. | x | x | ? |  | x | x | x | ? |  | x | x | [5 empty] | Jail List (List of inmates needed for court that day (New) and Booking Photos | Booking Data |  | Routing rules for Muni & Traffic and Juvenile Court? | https://github.com/CityOfNewOrleans/JTMP-Data-Exchange-Specs/blob/main/BookingExchange.md
2 | 5.3 | H | 1 | Y | 2024-06-25 | Release | Release | JMS |  |  | Release complete | x | x | ? |  | x | x | x | ? |  | x | x | [5 empty] | Inmate Release Dates | Inmate Release Information |  |  | https://github.com/CityOfNewOrleans/JTMP-Data-Exchange-Specs/blob/main/BookingExchange.md
0 | 0 | H | 2 | Y | 2024-11-15 | Charge Code Updates | Charge Table Update | Uniform Charge Table |  |  | Charge Code record add or update | x | x | x | x | x | x | x | x | [8 empty] | Uniform Charge Table Updates |  |  |  | https://github.com/CityOfNewOrleans/JTMP-Data-Exchange-Specs/blob/main/ChargeCodeUpdateExchange.md
33 | 8 | H | 3 | Y | 2024-12-11 | ChargeFiling | Charge Screening | Prosecutor by Karpel | City Attorney |  | Charges and Bill of Information or GJ Indictment (PDF) created in PBK | x | x | ? | [13 empty] | Screening Action Form and (Charge) Bill of Information | Screening Action Form |  | Confirm with i3 Verticals - impact on application config and roll-out? | JTMP-Data-Exchange-Specs/schemas/ChargeFiling_iepd/ChargeFiling.md at main · CityOfNewOrleans/JTMP-Data-Exchange-Specs
6 | 9 | H | 4 | Y | 2024-11-20 | New Case Initiation | Court Proceeding | District Court CMS | DigiCourt-Muni | DigiCourt-Juvenile | Allotment |  |  |  | x | x | x | x | ? |  | x | ? | [5 empty] | Charges & Dispositions | Court Case Number |  | Former Allotment List | https://github.com/CityOfNewOrleans/JTMP-Data-Exchange-Specs/blob/main/CaseInitiation.md
7 | 6.5 | H | 5 | Y | 2024-06-28 | Court Event | First Appearance | District Court CMS | DIgiCourt-Muni |  | Clerk schedules court event/hearing |  |  |  | x |  | x | x |  |  | x | [6 empty] | Case Events | Court Event |  |  | https://github.com/CityOfNewOrleans/JTMP-Data-Exchange-Specs/blob/main/CourtEventExchange.md
#REF! | 10.4 | H | 6 | Y | 2025-01-15 | Case-Charge Updates | Court Proceeding | District Court CMS | DigiCourt-Muni | DigiCourt-Juvenile | Clerk saves Changes to Parties, Charges, other Key Case Data |  |  |  | x | x | x | x | ? |  | x |  |  |  |  | x |  | Charges & Dispositions | Court Order |  | This needs to be a separate Charge-Disposition spec
9 | 12 | H | 7 | Y | 2024-11-20 | UniformCommitmentOrder | Court Proceeding | District Court CMS |  |  | Clerk dockets court order |  |  |  | x | x | x | x | ? |  |  | ? |  |  |  |  | x | Uniform Commitment Order | SentenceOrder |  |  | JTMP-Data-Exchange-Specs/schemas/UniformCommitmentOrder_iepd/UCO.md at main · CityOfNewOrleans/JTMP-Data-Exchange-Specs
10 | 6 and 10.1 | H | 8 | Y | 2024-06-27 | Court Order | First Appearance and Court Proceeding | District Court CMS | DIgiCourt-Muni | DigiCourt-Juvenile | Clerk dockets court order, including Bond Order |  |  |  | x |  | x | x | ? | [8 empty] | (Charge) Bond Amount & Type and Court Document Images and Supervision Orders | Bond Order, Court Order |  | Can this be general Court Order? | https://github.com/CityOfNewOrleans/JTMP-Data-Exchange-Specs/blob/main/CourtOrderExchange.md
11 | 11.3 | H | 9 | N | 2025-01-15 | Subpoena-Return Of Service | Subpoena | CourtNotify |  |  | Sheriff updates service in CourtNotify | x | x | [14 empty] | CourtNotify Subpoena Service |  |  | Confirm with i3 Verticals - impact on application config and roll-out?
12 | 5.2 | M | 10 | N | 2025-01-15 | Public Safety Assessment (PSA) | Pre-Trial Assessment | Pre-Trial Services (Dynamics) |  |  | PSA Complete or Supervisor Approval? |  | x | [14 empty] | N/A | Pretrial Services Assessment
13 |  | H | 11 | N |  | Subpoena (Note: Subp and RoS are the same exchange) |  | CourtNotify |  |  | Subpoena created in CourtNotify |  | x | [17 empty] | Confirm in i3 Verticals' contracted scope
14 | 10 | M | 11 | N | 2025-02-01 | Motions and Proposed Orders | Court Filing | Prosecutor by Karpel | DefenderData |  | Filing approved | ? | x | ? | [13 empty] | Court Filing | Court Filing
15 | 11.2 | L | 12 | N | 2025-10-01 | Subpoena Request | Subpoena Request | Prosecutor by Karpel | DefenderData |  | Subpoena created in CMS | x | [8 empty] | x | [6 empty] | CourtNotify Subpoenas | Subpeona
16 | 3.5 | H | 13 | N | 2024-11-18 | Arrest Report | Arrest | RMS |  |  | Supervisor approval |  |  |  | x | x | x | [10 empty] | Arrest Report | Face Sheet
17 | 3.1 | M | 14 | N | TBD | Warrant Issued | Arrest Warrant | CloudGavel |  |  | Judge approval | ? | ? | ? |  |  | x |  | ? |  |  | ? | [5 empty] | Arrest Warrant | Arrest Warrant
18 | 3.2 | M | 15 | N | TBD | Warrant Update | Arrest Warrant | RMS | DIgiCourt-Muni | District Court CMS | Warrant Cancel/Quash | [7 empty] | ? | x |  | x | [5 empty] | Warrant Updates (?) | Warrant Cancel
19 | 10.2 | M | 16 | N | TBD | Warrant Issued | Bench Warrant | District Court CMS | DigiCourt-Muni | DigiCourt-Juvenile | Judge issues bench warrant |  |  |  | ? |  |  |  | ? |  |  | x | [5 empty] | Bench Warrant | Bench Warrant
20 |  | Future | 17 | N | Added 10/24 | CrimeLabRequestResults | LIMS Testing Request | Prosecutor by Karpel | [15 empty] | x
20 |  | Future | 18 | N | Added 10/24 | VictimNotification |  | RMS | [8 empty] | x
22 |  | Future | 19 | Y | Added 11/24 | Personnel Updates | Personnel | RMS | Prosecutor by Karpel | DefenderData |  |  | x |  |  |  | x | ? |  |  | x | [9 empty] | Bulk vs transactional? What are the impacts on workflow at go-live for Clerks' Office?
23 | 11.4 | L | 20 | N | 2025-10-01 | Return of Service | Civil Process Service | CivilServe? |  |  | Return of Service or Service Attempt | x | x
23 | 2 | Future |  | N | 2025-08-01 | Incident (Offense) Report | Incident-Arrest | RMS | Sheriff Investigative Case Mgt |  | Supervisor approval | [16 empty] | Police Report | Police Report |  | Subscribers are recipients of Jail Packet today TBD whether Sheriff Investigative Case Mgt will publish jail incident reports
23 | 7 | Future |  | N | 2025-10-01 |  | Investigation |  |  |  | Request from DA | [16 empty] | Arrest Case Creation | Police Report
26 | 7.1 | N/A |  | N | 2025-10-01 |  | Digital Evidence Mgt |  |  |  | New A-Case case created | [16 empty] | 911 Call Recordings | 911 recording
27 | 7.2 | N/A |  | N | 2025-10-01 |  | Digital Evidence Mgt |  |  |  | Complete Certificate of Completeness | [16 empty] | Dispatch/ Police Reports | Police Report
28 | 7.3 | N/A |  | N | 2025-10-01 |  | Digital Evidence Mgt | [20 empty] | Body Camera Footage | Digital Evidence
29 |  | Future |  | N |  | Case Transfer | Bind-Over | DigiCourt-Muni |  |  | Bind-Over Charges to another court |  | ?
1 | 1 | N/A |  |  |  | CAD Incident | Dispatch | CAD |  |  | Law Enforcement Dispatched | [16 empty] | CAD Incident | CAD Incident
31 | 2.1 | N/A |  |  |  | Warrant Query | Query CASTNet | CASTNet |  |  | Send query | [16 empty] | Criminal History Queries | Query/Response
| 2.2 | N/A |  |  |  | CCH Query | Query LACCH | LACCH |  |  | Send query | [16 empty] | Criminal History Queries | Query/Response
32 | 3 | M |  |  |  | Warrant Request | Arrest Warrant |  |  |  | Officer requests warrant from within RMS | [8 empty] | x | [7 empty] | Warrant Request/Application | Arrest Register |  | New exchange with RMS?
34 | 5.1 | N/A |  |  |  | Pre-Trial Assessment (Probation Status) | Pre-Trial Assessment | Dept. of Corrections |  |  | Query | [7 empty] | ? | [8 empty] | Supervision Status | Probation and Parole Status |  | Query?
35 | 10 | N/A |  |  |  |  | Digital Evidence Mgt | Prosecutor by Karpel | Arrest Case Management | [8 empty] | x | [9 empty] | Discovery Documents
36 | 10.1 | N/A |  |  |  |  | Digital Evidence Mgt | Prosecutor by Karpel | Arrest Case Management | [8 empty] | x | [9 empty] | Body Camera Footage - Discovery | Digital Evidence
37 | 10.2 | N/A |  |  |  |  | Digital Evidence Mgt | Prosecutor by Karpel | Arrest Case Management | [8 empty] | x | [9 empty] | 911 Call Recordings - Discovery | 911 recording
38 | 10.3 | N/A |  |  |  |  | Digital Evidence Mgt | Arrest Case Management | [8 empty] | x | x | [9 empty] | Real Time Crime Camera Footage
39 | 11 | L |  |  |  | RosterUpdate | Subpoena |  | ADP |  | Officer schedule change | [9 empty] | x | [6 empty] | CourtNotify officer leave information
40 | 13 | L |  |  |  |  | Appeal | District Court CMS | DigiCourt-Muni |  | Clerk dockets court order | [16 empty] | Appeal
18%
Note on G3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This roadmap reference should be changed to jail booking information (we are talking basically about arrest registers). The jail list is something else entirely and is not separately listed. Note that we are currently deciding whether to use CourtNotify for the jail list function. That would eliminate the need for the i3 CMS to publish that information.
Note on AC3: Jim Pingel: This will be Booking Data; exchange replaces the need to generate a list (or augments it)
Note on AC6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Plus grand jury indictment and juvenile court waivers
Note on AC16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The publishing system will likely be CourtNotify, not the i3 CMS, at least in the near term. Subpoena and witness information would be pushed from CourtNotify to the i3 CMS and possible also consumed by the Karpel and OPD CMSs
Note on AC17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Does this include facesheet, gist, and warrant?
Note on I24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What is meant here?
Note on K25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not sure what this refers to.
Note on AC28: Jim Pingel: This may be a direct interface in RMS project
Note on AC32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should be more specific: not criminal history but warrant and warrant status
Note on I35: Jim Pingel: LA DOC would have to be the Publisher, or host a query service. This is not available at this time. It may be available with their new system. Check back with DOC
Note on AC41: Jim Pingel: Talk to Supreme Court about Apellate Court interface capabilities

## Critical Shared Identifiers
IdentifierType | Deprecate? | Traditional Name | Owning Agency | EDM Attribute Name | NIEM Element | NIEM Xpath | Arrest | Booking | ChargeFiling | CaseInitiation | Subpoena Return | Purpose
Person | FALSE | N/A | NOPD | Master Name Index Number |  | nc:CourtCase/j:CaseAugmentation/j:CaseDefendantParty/nc:EntityPerson/nola-ext:PersonAugmentation/nola-ext:PersonLocalIdentification/nc:IdentificationID | x | x | x | x |  | Mark43 will assign a Master Name Index (MNI) number to an individual. By sharing it, and tying it to a SID when available, we can begin to clean-up person identities, at least going forward with new arrests/
Person | FALSE | Employee Number | NOPD |  |  |  | x | x |  |  | x | Identifier assigned by the City payroll system. Unique to an individual, spans all employment assignments within the City's payroll system
Person | FALSE | SID | OPSO | Statewide ID (SID) | j:BookingSubject/RoleOfPerson/PersonStateIdentification/IdentificationID | nc:PersonStateIdentification/nc:IdentificationID | o | x | x | x |  | Uniquely identifies a person throughout their lifetime. Tied to fingerprints in the State's AFIS.
Person | FALSE | CCN | OPSO | Computer Control Identifier | nola-ext:PersonComputerControlIdentifier | /nola:BookingExchange/j:Booking/j:BookingSubject/RoleOfPerson/nola-ext:PersonAugmentation/nola-ext:PersonComputerControlIdentifier |  | x |  |  |  | Local equivalent of a SID. Generated at JMS at Pre-Booking process if subject does not have a prior arrest record in JMS OPSO. Otherwise, an existing CCN is assigned if prior arrests exist. Unique lifetime person ID used by NOPD and Sheriff.
Person | TRUE | Badge Number | NOPD |  |  |  | x | x |  |  | x | Badge assigned to officer. Not always unique to an individual
Person | TRUE | SCN | OPSO | Sheriff Control Number | /j:Booking/j:BookingAgencyRecordIdentification/IdentificationID | j:BookingAgencyRecordIdentification/IdentificationID |  | x |  |  |  | Unique ID for persons whose cases will be processed in Criminal Court. Number for life of an individual Issued to State level arrestee at the end of Booking process, if an SCN does not exist
Event | FALSE | Docket ID(?) | CDCC | Court Case Docket Number | /nc:CourtCase/nc:CaseDocketID |  |  |  |  | x |  | Case number assigned to a court case. Can be a Magistrate number, which may be replaced by a Criminal number when charges filed or billed in Criminal District Court
Event | FALSE | Item Number | NOPD | IncidentItemNumber | /Incident/ActivityIdentification/IdentificationID | /Incident/ActivityIdentification/IdentificationID | x | x | x | x |  | The incident number, assigned by the CAD system and carried through to the police incident/offense report. Traces a charge back to the appropriate inicent number in RMS for investigative follow-up and for Discovery.
Event | FALSE | Folder Number | OPSO | FolderNumber | j:BookingDocumentControlIdentification | j:Booking/j:BookingDocumentControlIdentification/IdentificationID |  | x | x | x |  | Uniquely identifies a single booking event and subsequent jail stay. New folder number generated for each new booking. Can include 1..* Arrest Register Numbers
Event | FALSE | Arrest Register Number | OPSO | Arrest Register Number | j:ArrestSequenceID | [6 empty] | Assigned at booking to each Item Number; 1..* Arrest Numbers per Folder
Event | FALSE | ATN | OPSO | ArrestTrackingNumber | /j:ArrestCharge/j:ChargeTrackingIdentification/IdentificationID | j:Arrest/j:ArrestCharge//nola-ext:ChargeAugmentation/nola-ext:StatewideArrestTrackingNumber |  | x | x | x |  | Generated by the LA State Police-AFIS system. It is the unique identifier for a specific Booking event.
Charge | FALSE | ChargeKey | NOPD | ChargeKey | nola-ext:ChargeKey | j:Charge/nola-ext:ChargeAugmentation/nola-ext:ChargeKey | x | x | x | x |  | Standardizes charging details. Drawn from the Parish Uniform Charge Table.
Charge | FALSE |  | OPSO | ChargeSequenceNumber | nola-ext:StatewideATNChargeSequenceID | nola-ext:StatewideATNChargeSequenceID |  | x | x | x |  | Associated with the ATN - each booked charge gets a unique ID. The combination of ATN and Sequence No uniquely identify a charge. It should stay associated with that charge throughout the justice system.

## Lookups
Lookup:Application | Agency | Agency Acronym | Vendor | System/Vendor |  | Lookup: Data Objects
Arrest Case Management | 911-Dispatch | OPCD | ADP |  | Person | 911 recording
AS400 | City IT | ITI | Axon |  | Event | 911 Transcripts
CAD | Criminal District Clerk of Court | CDCC | Beacon |  | Charge | A-Case Data Request
CAJIN | Criminal District Court | CDC | CDC |  |  | Allotment List
CASTNet | Dept of Corrections | DOC | DigiComm |  |  | Arrest Register
City Attorney | District Attorney | OPDA | DigiComm |  |  | Arrest Warrant
CivilServe? | Juvenile Court | OJC | FusionStax |  |  | Arrest Warrant Application
CloudGavel | Louisana Supreme Court | LA SP | i3 Verticals |  |  | Bench Warrant
CourtNotify | Muncipal & Traffic Court | MTCNO | ITI |  |  | Bill of Information
DefenderData | Police Department | NOPD | JusticeWorks |  |  | Bond Instrument
DigiCourt-Juvenile | Public Defender | OPD | Karpel |  |  | Bond Order
DigiCourt-Muni | Sheriff's Office | OPSO | Mark43 |  |  | Booking Data
District Court CMS | City of New Orleans | CNO | Motorola |  |  | Booking Photos
DocketMaster |  |  | Orion |  |  | Boykin Form
EPR |  |  | SoundThinking |  |  | CAD Incident
evidence.com |  |  | State of LA |  |  | Cancellation Bulletin
JMS |  |  | Tyler Technologies |  |  | Certificate of Completeness
LACCH | [5 empty] | Court Case Number
Payroll System | [5 empty] | Court Event
Pre-Trial Services (Dynamics) | [5 empty] | Court Filing
Prosecutor by Karpel | [5 empty] | Court Order
RMS | [5 empty] | Crime Lab Reports
Sheriff Investigative Case Mgt | [5 empty] | Criminal History
Uniform Charge Table | [5 empty] | DA Intake Notice
Digital Evidence Links
DWI Data
Evidence List
Evidence Report Links
Evidence Test Request
Face Sheet
Gist
Hold Request/Detainer
Inmate Release Information
Investigative Report
Magistrate List
Motion Exchange
Motion Exchange for Open Court
Municipal Citations
NIST Record
Plea Deal
Plea Rejection
Police Report
Pretrial Services Assessment
Probation and Parole Status
Property
Proposed Protective Order
Protective Order
Query/Response
RAP Sheet
Rejected Warrant
Release Orders
Return of Service
ROR
Screening Action Form
SentenceOrder
Service Notification
Statewide Booking List
Subpeona
Supplemental EPR
Supplemental Reports
Unapproved Incident Report
Updated Bill of Information
Verbal Incident Update
Victim Information
Warant Cancel
Warrant Cancel
Warrant Clear
Warrant Inquiry
Warrant Recall
Warrant Recall Request
Witness List

## System-Agency-Vendor Matrix
System | Owner Agency | Vendor | ApplicationType
CAD | OPCD | Motorola | CAD
CASTNet | ITI | ITI | Crim History
CloudGavel | NOPD | FusionStax | Warrant
CourtNotify | NOPD | Orion | Subpoena
DefenderData | OPD | JusticeWorks | CMS
CAJIN | DOC | State of LA | OMS
DigiCourt-Muni | MCTNO | DigiComm | CMS
DigiCourt-Juvenile | OJC | DigiComm | CMS
District Court CMS | CDCC | i3 Verticals | CMS
JMS | OPSO | Beacon | JMS
Pre-Trial Services (Dynamics) | CDC | CDC | CMS
Prosecutor by Karpel | OPDA | Karpel | CMS
RMS | NOPD | Mark43 | RMS